## Sheet1
Components | Tasks | Assigned to | Start Date | End Date | Days | Status
EDA | train+spray | Leonard | 2020-07-03 | 2020-07-09 | 7 days | Completed
| train+spray | Pallavi | 2020-07-03 | 2020-07-09 | 7 days | Completed
| train+weather | Melvin | 2020-07-03 | 2020-07-09 | 7 days | Completed
Feature engineering |  | Leonard | 2020-07-10 | 2020-07-10 | 1 day | Completed
Modelling | Preprocessing & Modelling | Melvin | 2020-07-10 | 2020-07-11 | 2 days | Completed
Cost-Benefit Analysis (CBA) |  | Leonard | 2020-07-10 | 2020-07-11 | 2 dyas | Completed
Presentation |  | Leonard, Melvin, Pallavi | 2020-07-11 | 2020-07-12 | 2 days | Completed